## Gantt
Pattern x Brand — TikTok Shop 1P Onboarding (Existing Shop, Subaccount Access)
Bar colour = owner: Pattern (orange) · Brand (green) · Pattern/Brand joint (blue). Edit the Start and Due columns to move a bar; the chart redraws automatically. Scenario: TikTok Shop 1P — Existing Shop, Subaccount Access.
[9 empty] | Aug | [27 empty] | Sep | [29 empty] | Oct
 | time axis 2026-08-04 to 2026-10-14
Category | Action # | Task | Owner | Start | Due | Days | Status | Notes | time axis 2026-08-04 to 2026-10-14
Subaccount Access
Subaccount Access | 1 | Onboarding package generated and sent to brand | Pattern | 2026-08-04 | 2026-08-05 | 2 | Not Started
Subaccount Access | 2 | Wholesale pricing gathered from brand | Brand | 2026-08-05 | 2026-08-06 | 2 | Not Started
Subaccount Access | 3 | Brand shares existing shop details (shop code/URL) and documents | Brand | 2026-08-06 | 2026-08-07 | 2 | Not Started
Subaccount Access | 4 | OPM assigned; onboarding logged in Asana | Pattern | 2026-08-07 | 2026-08-07 | 1 | Not Started
Subaccount Access | 5 | SCM/AM assigned | Pattern | 2026-08-07 | 2026-08-08 | 2 | Not Started
Subaccount Access | 6 | Brand invites Pattern as a Seller Center subaccount (roles & permissions) | Brand | 2026-08-08 | 2026-08-09 | 2 | Not Started
Subaccount Access | 7 | Invite and OTP verification completed | Brand | 2026-08-09 | 2026-08-09 | 1 | Not Started
Subaccount Access | 8 | OPM accepts invite; access scope verified | Pattern | 2026-08-09 | 2026-08-09 | 1 | Not Started
Subaccount Access | 9 | Shop code shared for SKM verification | Pattern | 2026-08-09 | 2026-08-09 | 1 | Not Started
Subaccount Access | 10 | Marketplace Seller record updated on Shelf; Connect integration completed | Pattern | 2026-08-09 | 2026-08-11 | 3 | Not Started
Subaccount Access | 11 | Existing CQ/BA coverage confirmed for all listed product categories | Pattern | 2026-08-11 | 2026-08-12 | 2 | Not Started
Subaccount Access | 12 | Any uncovered category applied for (if needed) | Pattern/Brand | 2026-08-12 | 2026-08-15 | 4 | Not Started
Subaccount Access | 13 | Final audit requested and completed | Pattern | 2026-08-15 | 2026-08-16 | 2 | Not Started
Subaccount Access | 14 | Brand marked Live/Active | Pattern | 2026-08-16 | 2026-08-16 | 1 | Not Started
Subaccount Access | 15 | TikTok handle connected | Pattern | 2026-08-16 | 2026-08-17 | 2 | Not Started
Subaccount Access | 16 | Euka and IPPC accounts created | Pattern | 2026-08-17 | 2026-08-18 | 2 | Not Started
Operations
Operations | 1 | Send existing Product Listing details listed in shop | Brand | 2026-08-04 | 2026-08-04 | 1 | Not Started
Operations | 2 | Create Brand in Shelf and list all products | Pattern | 2026-08-04 | 2026-08-07 | 4 | Not Started
Operations | 3 | Set up Connect integration for Brand shop with placeholder | Pattern | 2026-08-07 | 2026-08-07 | 1 | Not Started
Operations | 4 | Complete Connect integration and Brand shop connection | Pattern | 2026-08-07 | 2026-08-14 | 8 | Not Started
Operations | 5 | Double-check listed products in shop match the assortment in Shelf | Pattern | 2026-08-14 | 2026-08-17 | 4 | Not Started
Operations | 6 | Gather re-approval documents | Brand | 2026-08-17 | 2026-08-17 | 1 | Not Started
Operations | 7 | Re-approval documents submitted | Pattern | 2026-08-17 | 2026-08-18 | 2 | Not Started
Operations | 8 | Brand Authorization & Category Qualification re-approved | Pattern | 2026-08-18 | 2026-08-21 | 4 | Not Started
Operations | 9 | Once BA & CQ is done, push the products live | Brand | 2026-08-21 | 2026-08-24 | 4 | Not Started
Operations | 10 | Map product SKUs to Shelf as per Brand shop SKUs | Pattern | 2026-08-24 | 2026-08-24 | 1 | Not Started
Operations | 11 | Place test order to check flow | Pattern | 2026-08-24 | 2026-08-24 | 1 | Not Started
Operations | 12 | Confirm order details are flowing to required teams & POCs | Pattern | 2026-08-24 | 2026-08-28 | 5 | Not Started
Merchandising
Merchandising | 1 | Align on new hero SKUs | Pattern/Brand | 2026-08-04 | 2026-08-07 | 4 | Not Started
Merchandising | 2 | Align on bundles (see Pattern recommendations in the H2 plan) | Pattern/Brand | 2026-08-07 | 2026-08-07 | 1 | Not Started
Merchandising | 3 | Gather image/copy assets for new hero SKUs and bundles | Brand | 2026-08-07 | 2026-08-10 | 4 | Not Started
Merchandising | 4 | Audit existing live SKUs | Pattern | 2026-08-10 | 2026-08-14 | 5 | Not Started
Merchandising | 5 | Build and optimize listings for new hero SKUs and bundles | Pattern | 2026-08-14 | 2026-08-21 | 8 | Not Started
Merchandising | 6 | Optimize listing combinations | Pattern/Brand | 2026-08-21 | 2026-08-21 | 1 | Not Started
Merchandising | 7 | Confirm free shipping | Pattern | 2026-08-21 | 2026-08-21 | 1 | Not Started
Merchandising | 8 | Confirm discount floors for all SKUs and bundles | Brand | 2026-08-21 | 2026-08-21 | 1 | Not Started
Merchandising | 9 | Align on discount calendar | Pattern/Brand | 2026-08-21 | 2026-08-26 | 6 | Not Started
Affiliate
Affiliate | 1 | Send existing briefs | Brand | 2026-08-04 | 2026-08-04 | 1 | Not Started
Affiliate | 2 | Send existing affiliate partnership info - who are the top affiliates | Brand | 2026-08-04 | 2026-08-04 | 1 | Not Started
Affiliate | 3 | Send existing affiliate partnership info - what are we offering top affiliates (increased commissions, retainer fees, challenges, etc.) | Brand | 2026-08-04 | 2026-08-04 | 1 | Not Started
Affiliate | 4 | Send existing affiliate partnership info - is there a community channel (e.g. Discord) and who runs it | Brand | 2026-08-04 | 2026-08-04 | 1 | Not Started
Affiliate | 5 | Send existing affiliate partnership info - what is brand involvement with top affiliates, webinars, etc. | Brand | 2026-08-04 | 2026-08-04 | 1 | Not Started
Affiliate | 6 | Product education session - Pattern team learns what makes the products unique | Brand | 2026-08-04 | 2026-08-07 | 4 | Not Started
Affiliate | 7 | Find 20 new L3+ creators for launch (target 40 total videos) | Pattern | 2026-08-07 | 2026-08-10 | 4 | Not Started
Affiliate | 8 | 20 new L3+ creator samples sent | Pattern | 2026-08-10 | 2026-08-11 | 2 | Not Started
Affiliate | 9 | Review and optimize existing briefs | Pattern | 2026-08-11 | 2026-08-21 | 11 | Not Started
Affiliate | 10 | Create new briefs for new hero SKUs | Pattern | 2026-08-21 | 2026-08-21 | 1 | Not Started
Affiliate | 11 | Finalize outreach messaging (Euka, email <L3, email >L3, Pattern retainer L4+) | Pattern | 2026-08-21 | 2026-08-21 | 1 | Not Started
Affiliate | 12 | Engage top 10-30 creators for retainers where applicable | Pattern | 2026-08-21 | 2026-08-21 | 1 | Not Started
Affiliate | 13 | Launch outreach | Pattern | 2026-08-21 | 2026-08-28 | 8 | Not Started
Affiliate | 14 | Existing creator retainers solidified | Pattern | 2026-08-28 | 2026-08-28 | 1 | Not Started
Affiliate | 15 | 20 new L3+ creator videos live | Pattern | 2026-08-28 | 2026-08-28 | 1 | Not Started
Inventory
Inventory | 1 | Create demand plan for existing SKUs | Pattern | 2026-08-04 | 2026-08-07 | 4 | Not Started
Inventory | 2 | Create demand plan for new hero SKUs and bundles | Pattern | 2026-08-07 | 2026-08-07 | 1 | Not Started
Inventory | 3 | Combine demand plan with Amazon Business (if applicable) | Pattern | 2026-08-07 | 2026-08-11 | 5 | Not Started
Inventory | 4 | Internal setup complete for all products | Pattern | 2026-08-11 | 2026-08-11 | 1 | Not Started
Inventory | 5 | Cut PO for new hero SKUs, bundles, and any needed inventory for existing SKUs | Pattern | 2026-08-11 | 2026-08-14 | 4 | Not Started
Inventory | 6 | New inventory received at Pattern | Pattern | 2026-08-14 | 2026-08-27 | 14 | Not Started
Inventory | 7 | Cut PO for all products for FBT | Pattern | 2026-08-27 | 2026-09-29 | 34 | Not Started
Inventory | 8 | New inventory received at FBT | Pattern | 2026-09-29 | 2026-10-14 | 16 | Not Started
Advertising
Advertising | 1 | Change advertising partnership type from Other to Media Agency | Pattern | 2026-08-04 | 2026-08-26 | 23 | Not Started
Advertising | 2 | Approve partnership change | Brand | 2026-08-26 | 2026-08-27 | 2 | Not Started
Advertising | 3 | Confirm advertising operations | Pattern | 2026-08-27 | 2026-08-28 | 2 | Not Started
Advertising | 4 | Launch ads | Pattern | 2026-08-28 | 2026-08-28 | 1 | Not Started
Brand Handles
Brand Handles | 1 | Confirm marketing account structure (must include LIVE and AIGC) | Pattern/Brand | 2026-08-04 | 2026-08-14 | 11 | Not Started
Brand Handles | 2 | Launch additional marketing accounts needed | Brand | 2026-08-14 | 2026-08-21 | 8 | Not Started
Brand Handles | 3 | Link marketing accounts | Pattern/Brand | 2026-08-21 | 2026-08-26 | 6 | Not Started
Brand Handles | 4 | Align on plan for LIVE and AIGC content for marketing accounts | Pattern/Brand | 2026-08-26 | 2026-08-28 | 3 | Not Started