## Gantt
Pattern x Brand — TikTok Shop 3P Onboarding (Existing TTS, EIN Transfer)
Bar colour = owner: Pattern (orange) · Brand (green) · Pattern/Brand joint (blue). Edit the Start and Due columns to move a bar; the chart redraws automatically. Scenario: TikTok Shop 3P — Existing TTS needs EIN Transfer.
[9 empty] | Aug | [27 empty] | Sep | [29 empty] | Oct
 | time axis 2026-08-04 to 2026-10-15
Category | Action # | Task | Owner | Start | Due | Days | Status | Notes | time axis 2026-08-04 to 2026-10-15
EIN Transfer
EIN Transfer | 1 | Onboarding package generated and sent to brand | Pattern | 2026-08-04 | 2026-08-05 | 2 | Not Started
EIN Transfer | 2 | Wholesale pricing gathered from brand | Brand | 2026-08-05 | 2026-08-06 | 2 | Not Started
EIN Transfer | 3 | Brand completes onboarding package (Shelf/PIS) with product and pricing details | Brand | 2026-08-06 | 2026-08-07 | 2 | Not Started
EIN Transfer | 4 | Eligibility checklist confirmed (shop status, withdrawals, holiday mode, OTP) | Pattern/Brand | 2026-08-07 | 2026-08-10 | 4 | Not Started
EIN Transfer | 5 | OPM assigned; onboarding logged in Asana | Pattern | 2026-08-10 | 2026-08-10 | 1 | Not Started
EIN Transfer | 6 | SCM assigned | Pattern | 2026-08-10 | 2026-08-11 | 2 | Not Started
EIN Transfer | 7 | Seller Center owner access obtained or transferred | Brand | 2026-08-11 | 2026-08-12 | 2 | Not Started
EIN Transfer | 8 | New owner (Pattern) entity information submitted to TikTok | Pattern | 2026-08-12 | 2026-08-18 | 7 | Not Started
EIN Transfer | 9 | Novation Agreement signed and uploaded | Pattern/Brand | 2026-08-18 | 2026-08-20 | 3 | Not Started
EIN Transfer | 10 | Entity transfer submitted for TikTok review | Pattern | 2026-08-20 | 2026-08-20 | 1 | Not Started
EIN Transfer | 11 | TikTok review completed (approved, or corrections resubmitted) | Pattern | 2026-08-20 | 2026-08-29 | 10 | Not Started
EIN Transfer | 12 | New bank account bound under Pattern's entity | Pattern | 2026-08-29 | 2026-08-30 | 2 | Not Started
EIN Transfer | 13 | Brand Authorization and Category Qualification re-applied under Pattern's entity | Pattern | 2026-08-30 | 2026-09-02 | 4 | Not Started
EIN Transfer | 14 | BA/CQ re-approved; affected products reactivated | Pattern | 2026-09-02 | 2026-09-07 | 6 | Not Started
EIN Transfer | 15 | Shelf listing and finance approval completed | Pattern | 2026-09-07 | 2026-09-10 | 4 | Not Started
EIN Transfer | 16 | Old SKUs removed from Connect; listings mapped to Pattern SKUs | Pattern | 2026-09-10 | 2026-09-12 | 3 | Not Started
EIN Transfer | 17 | Sync verified across Shelf, TikTok Shop, and Connect | Pattern | 2026-09-12 | 2026-09-13 | 2 | Not Started
EIN Transfer | 18 | Inventory confirmed with Inventory POC | Pattern | 2026-09-13 | 2026-09-13 | 1 | Not Started
EIN Transfer | 19 | Fulfillment go-live | Pattern | 2026-09-13 | 2026-09-13 | 1 | Not Started
EIN Transfer | 20 | Previous agency unlinked; TikTok handle connected | Pattern | 2026-09-13 | 2026-09-14 | 2 | Not Started
EIN Transfer | 21 | Euka and IPPC accounts created | Pattern | 2026-09-14 | 2026-09-15 | 2 | Not Started
Operations
Operations | 1 | Send existing Product Listing details listed in shop | Brand | 2026-08-04 | 2026-08-04 | 1 | Not Started
Operations | 2 | Create Brand in Shelf and list all products | Pattern | 2026-08-04 | 2026-08-07 | 4 | Not Started
Operations | 3 | Set up Connect integration for Brand shop with placeholder | Pattern | 2026-08-07 | 2026-08-07 | 1 | Not Started
Operations | 4 | Complete Connect integration and Brand shop connection | Pattern | 2026-08-07 | 2026-08-14 | 8 | Not Started
Operations | 5 | Double-check listed products in shop match the assortment in Shelf | Pattern | 2026-08-14 | 2026-08-17 | 4 | Not Started
Operations | 6 | Gather re-approval documents | Brand | 2026-08-17 | 2026-08-17 | 1 | Not Started
Operations | 7 | Re-approval documents submitted | Pattern | 2026-08-17 | 2026-08-18 | 2 | Not Started
Operations | 8 | Brand Authorization & Category Qualification re-approved | Pattern | 2026-08-18 | 2026-08-21 | 4 | Not Started
Operations | 9 | Once BA & CQ is done, push the products live | Brand | 2026-08-21 | 2026-08-24 | 4 | Not Started
Operations | 10 | Map product SKUs to Shelf as per Brand shop SKUs | Pattern | 2026-08-24 | 2026-08-24 | 1 | Not Started
Operations | 11 | Place test order to check flow | Pattern | 2026-08-24 | 2026-08-24 | 1 | Not Started
Operations | 12 | Confirm order details are flowing to required teams & POCs | Pattern | 2026-08-24 | 2026-08-28 | 5 | Not Started
Merchandising
Merchandising | 1 | Align on new hero SKUs | Pattern/Brand | 2026-08-04 | 2026-08-07 | 4 | Not Started
Merchandising | 2 | Align on bundles (see Pattern recommendations in the H2 plan) | Pattern/Brand | 2026-08-07 | 2026-08-07 | 1 | Not Started
Merchandising | 3 | Gather image/copy assets for new hero SKUs and bundles | Brand | 2026-08-07 | 2026-08-10 | 4 | Not Started
Merchandising | 4 | Audit existing live SKUs | Pattern | 2026-08-10 | 2026-08-14 | 5 | Not Started
Merchandising | 5 | Build and optimize listings for new hero SKUs and bundles | Pattern | 2026-08-14 | 2026-08-21 | 8 | Not Started
Merchandising | 6 | Optimize listing combinations | Pattern/Brand | 2026-08-21 | 2026-08-21 | 1 | Not Started
Merchandising | 7 | Confirm free shipping | Pattern | 2026-08-21 | 2026-08-21 | 1 | Not Started
Merchandising | 8 | Confirm discount floors for all SKUs and bundles | Brand | 2026-08-21 | 2026-08-21 | 1 | Not Started
Merchandising | 9 | Align on discount calendar | Pattern/Brand | 2026-08-21 | 2026-08-26 | 6 | Not Started
Affiliate
Affiliate | 1 | Send existing briefs | Brand | 2026-08-04 | 2026-08-04 | 1 | Not Started
Affiliate | 2 | Send existing affiliate partnership info - who are the top affiliates | Brand | 2026-08-04 | 2026-08-04 | 1 | Not Started
Affiliate | 3 | Send existing affiliate partnership info - what are we offering top affiliates (increased commissions, retainer fees, challenges, etc.) | Brand | 2026-08-04 | 2026-08-04 | 1 | Not Started
Affiliate | 4 | Send existing affiliate partnership info - is there a community channel (e.g. Discord) and who runs it | Brand | 2026-08-04 | 2026-08-04 | 1 | Not Started
Affiliate | 5 | Send existing affiliate partnership info - what is brand involvement with top affiliates, webinars, etc. | Brand | 2026-08-04 | 2026-08-04 | 1 | Not Started
Affiliate | 6 | Product education session - Pattern team learns what makes the products unique | Brand | 2026-08-04 | 2026-08-07 | 4 | Not Started
Affiliate | 7 | Find 20 new L3+ creators for launch (target 40 total videos) | Pattern | 2026-08-07 | 2026-08-10 | 4 | Not Started
Affiliate | 8 | 20 new L3+ creator samples sent | Pattern | 2026-08-10 | 2026-08-11 | 2 | Not Started
Affiliate | 9 | Review and optimize existing briefs | Pattern | 2026-08-11 | 2026-08-21 | 11 | Not Started
Affiliate | 10 | Create new briefs for new hero SKUs | Pattern | 2026-08-21 | 2026-08-21 | 1 | Not Started
Affiliate | 11 | Finalize outreach messaging (Euka, email <L3, email >L3, Pattern retainer L4+) | Pattern | 2026-08-21 | 2026-08-21 | 1 | Not Started
Affiliate | 12 | Engage top 10-30 creators for retainers where applicable | Pattern | 2026-08-21 | 2026-08-21 | 1 | Not Started
Affiliate | 13 | Launch outreach | Pattern | 2026-08-21 | 2026-08-28 | 8 | Not Started
Affiliate | 14 | Existing creator retainers solidified | Pattern | 2026-08-28 | 2026-08-28 | 1 | Not Started
Affiliate | 15 | 20 new L3+ creator videos live | Pattern | 2026-08-28 | 2026-08-28 | 1 | Not Started
Inventory
Inventory | 1 | Create demand plan for existing SKUs | Pattern | 2026-08-04 | 2026-08-07 | 4 | Not Started
Inventory | 2 | Create demand plan for new hero SKUs and bundles | Pattern | 2026-08-07 | 2026-08-07 | 1 | Not Started
Inventory | 3 | Combine demand plan with Amazon Business (if applicable) | Pattern | 2026-08-07 | 2026-08-11 | 5 | Not Started
Inventory | 4 | Internal setup complete for all products | Pattern | 2026-08-11 | 2026-08-11 | 1 | Not Started
Inventory | 5 | Cut PO for new hero SKUs, bundles, and any needed inventory for existing SKUs | Pattern | 2026-08-11 | 2026-08-14 | 4 | Not Started
Inventory | 6 | Verify inventory quantities at FBT ahead of the EIN transfer | Brand | 2026-08-14 | 2026-08-14 | 1 | Not Started
Inventory | 7 | Cut PO for necessary inventory at FBT ahead of the EIN transfer | Pattern | 2026-08-14 | 2026-08-14 | 1 | Not Started
Inventory | 8 | Work with FBT to return remaining FBT inventory to Brand | Pattern | 2026-08-14 | 2026-08-15 | 2 | Not Started
Inventory | 9 | New inventory received at Pattern | Pattern | 2026-08-15 | 2026-08-28 | 14 | Not Started
Inventory | 10 | Cut PO for all products for FBT | Pattern | 2026-08-28 | 2026-09-30 | 34 | Not Started
Inventory | 11 | New inventory received at FBT | Pattern | 2026-09-30 | 2026-10-15 | 16 | Not Started
Advertising
Advertising | 1 | Change advertising partnership type from Other to Media Agency | Pattern | 2026-08-04 | 2026-08-26 | 23 | Not Started
Advertising | 2 | Approve partnership change | Brand | 2026-08-26 | 2026-08-27 | 2 | Not Started
Advertising | 3 | Confirm advertising operations | Pattern | 2026-08-27 | 2026-08-28 | 2 | Not Started
Advertising | 4 | Launch ads | Pattern | 2026-08-28 | 2026-08-28 | 1 | Not Started
Brand Handles
Brand Handles | 1 | Confirm marketing account structure (must include LIVE and AIGC) | Pattern/Brand | 2026-08-04 | 2026-08-14 | 11 | Not Started
Brand Handles | 2 | Launch additional marketing accounts needed | Brand | 2026-08-14 | 2026-08-21 | 8 | Not Started
Brand Handles | 3 | Link marketing accounts | Pattern/Brand | 2026-08-21 | 2026-08-26 | 6 | Not Started
Brand Handles | 4 | Align on plan for LIVE and AIGC content for marketing accounts | Pattern/Brand | 2026-08-26 | 2026-08-28 | 3 | Not Started