## Gain
Pattern x Brand — TikTok Shop 3P Onboarding (New TTS Shop Create)
Bar colour = owner: Pattern (orange) · Brand (green) · Pattern/Brand joint (blue). Edit the Start and Due columns to move a bar; the chart redraws automatically. Scenario: TikTok Shop 3P — New Shop, Pattern creates the TTS shop (Internal Onboarding SOP section 1, updated 07/31/2026). Dates assume a placeholder Day 0 of 09/08/2026.
[9 empty] | Sep | [22 empty] | Oct | [30 empty] | Nov
 | time axis 2026-09-08 to 2026-11-21
Category | Action # | Task | Owner | Start | Due | Days | Status | Notes | time axis 2026-09-08 to 2026-11-21
Shop Creation
Shop Creation | 1 | Onboarding package generated and sent to brand | Pattern | 2026-09-08 | 2026-09-09 | 2 | Not Started
Shop Creation | 2 | Wholesale price for brand SKUs provided to SCM | Brand | 2026-09-09 | 2026-09-10 | 2 | Not Started
Shop Creation | 3 | Brand returns completed onboarding package + supporting documents | Brand | 2026-09-10 | 2026-09-11 | 2 | Not Started
Shop Creation | 4 | Sales submits Asana onboarding form; OPM assigned by Operations | Pattern | 2026-09-11 | 2026-09-11 | 1 | Not Started
Shop Creation | 5 | SCM assigned to the brand (Adam) | Pattern | 2026-09-12 | 2026-09-12 | 1 | Not Started
Shop Creation | 6 | OPM confirms TikTok team routing (which TT team owns the brand) | Pattern | 2026-09-12 | 2026-09-12 | 1 | Not Started
Shop Creation | 7 | OPM requests onboarding link from the confirmed TikTok team | Pattern | 2026-09-12 | 2026-09-14 | 3 | Not Started
Shop Creation | 8 | Brand email created and whitelisted by TTS | Pattern | 2026-09-15 | 2026-09-16 | 2 | Not Started
Shop Creation | 9 | Shop created; warehouse, tax and finance info completed | Pattern | 2026-09-16 | 2026-09-19 | 4 | Not Started
Shop Creation | 10 | Shop deactivation issues resolved with TikTok Support (Feiyan), if any | Pattern | 2026-09-19 | 2026-09-21 | 3 | Not Started
Shop Creation | 11 | Shop code + proof sent to Catherine Hu for SKM verification | Pattern | 2026-09-21 | 2026-09-21 | 1 | Not Started
Shop Creation | 12 | Category Qualification (CQ) + Brand Authorization (BA) applications submitted | Pattern | 2026-09-21 | 2026-09-23 | 3 | Not Started
Shop Creation | 13 | Brand supplies corrected authorization docs if CQ/BA rejected | Brand | 2026-09-23 | 2026-09-25 | 3 | Not Started
Shop Creation | 14 | CQ + BA approved (escalate to TikTok Support if still unresolved) | Pattern/Brand | 2026-09-25 | 2026-09-28 | 4 | Not Started
Shop Creation | 15 | Final audit requested from Ops Team Lead (Sanskar Sant) | Pattern | 2026-10-08 | 2026-10-09 | 2 | Not Started
Shop Creation | 16 | Brand marked Live/Active; onboarding task marked complete | Pattern | 2026-10-09 | 2026-10-09 | 1 | Not Started
Shop Creation | 17 | TikTok handle connected | Pattern | 2026-10-09 | 2026-10-10 | 2 | Not Started
Shop Creation | 18 | Customer Support + Account Health emails added to shop; teams notified | Pattern | 2026-10-09 | 2026-10-10 | 2 | Not Started
Shop Creation | 19 | Brand binding completed with AM (Catherine Hu) | Pattern | 2026-10-10 | 2026-10-12 | 3 | Not Started
Shop Creation | 20 | SCM files Ops task; Euka and IPPC accounts created | Pattern | 2026-10-12 | 2026-10-13 | 2 | Not Started
Operations
Operations | 1 | Brand shares full product / SKU details (PIS) for listing | Brand | 2026-09-10 | 2026-09-11 | 2 | Not Started
Operations | 2 | Brand created in Shelf; Master Products and Shelf listings created | Pattern | 2026-09-11 | 2026-09-15 | 5 | Not Started
Operations | 3 | Connect integration set up for brand shop with placeholder | Pattern | 2026-09-15 | 2026-09-15 | 1 | Not Started
Operations | 4 | Marketplace Seller record updated on Shelf; Connect integration completed | Pattern | 2026-09-19 | 2026-09-21 | 3 | Not Started
Operations | 5 | TTS marketplace listings created | Pattern | 2026-09-28 | 2026-10-01 | 4 | Not Started
Operations | 6 | Shelf listings updated with marketplace listing so both stay in sync | Pattern | 2026-10-01 | 2026-10-02 | 2 | Not Started
Operations | 7 | Inventory sync started once inventory arrives; sync issues resolved with Fulfillment | Pattern | 2026-10-05 | 2026-10-08 | 4 | Not Started
Operations | 8 | Confirm order details are flowing to required teams & POCs | Pattern | 2026-10-08 | 2026-10-09 | 2 | Not Started
Inventory
Inventory | 1 | Create demand plan for launch SKUs and bundles | Pattern | 2026-09-11 | 2026-09-14 | 4 | Not Started
Inventory | 2 | SCM confirms wholesale price and gets Finance sign-off (Asana form) | Pattern | 2026-09-15 | 2026-09-17 | 3 | Not Started
Inventory | 3 | SCM places initial PO with John (Asana form) | Pattern | 2026-09-17 | 2026-09-18 | 2 | Not Started
Inventory | 4 | Brand ships inventory to Pattern warehouse | Brand | 2026-09-18 | 2026-09-28 | 11 | Not Started
Inventory | 5 | Inventory received at Pattern | Pattern | 2026-09-28 | 2026-10-05 | 8 | Not Started
Inventory | 6 | Cut PO for all products for FBT | Pattern | 2026-10-05 | 2026-10-28 | 24 | Not Started
Inventory | 7 | Inventory received at FBT | Pattern | 2026-10-28 | 2026-11-09 | 13 | Not Started
Merchandising
Merchandising | 1 | Align on launch hero SKUs | Pattern/Brand | 2026-09-08 | 2026-09-11 | 4 | Not Started
Merchandising | 2 | Align on bundles | Pattern/Brand | 2026-09-11 | 2026-09-11 | 1 | Not Started
Merchandising | 3 | Gather image / copy assets for hero SKUs and bundles | Brand | 2026-09-11 | 2026-09-14 | 4 | Not Started
Merchandising | 4 | Build and optimize listings for hero SKUs and bundles | Pattern | 2026-09-18 | 2026-09-25 | 8 | Not Started
Merchandising | 5 | Optimize listing combinations | Pattern/Brand | 2026-09-25 | 2026-09-28 | 4 | Not Started
Merchandising | 6 | Confirm free shipping | Pattern | 2026-09-25 | 2026-09-25 | 1 | Not Started
Merchandising | 7 | Confirm discount floors for all SKUs and bundles | Brand | 2026-09-25 | 2026-09-25 | 1 | Not Started
Merchandising | 8 | Align on discount calendar | Pattern/Brand | 2026-09-25 | 2026-09-30 | 6 | Not Started
Affiliate
Affiliate | 1 | Share existing creator briefs and affiliate program info, if any (top affiliates, offers, community channel, brand involvement) | Brand | 2026-09-08 | 2026-09-09 | 2 | Not Started
Affiliate | 2 | Product education session - Pattern team learns what makes the products unique | Brand | 2026-09-08 | 2026-09-11 | 4 | Not Started
Affiliate | 3 | Find 20 new L3+ creators for launch (target 40 total videos) | Pattern | 2026-09-14 | 2026-09-21 | 8 | Not Started
Affiliate | 4 | Create briefs for hero SKUs | Pattern | 2026-09-21 | 2026-09-28 | 8 | Not Started
Affiliate | 5 | Finalize outreach messaging (Euka, email <L3, email >L3, Pattern retainer L4+) | Pattern | 2026-09-28 | 2026-09-28 | 1 | Not Started
Affiliate | 6 | Creator samples sent (20 new L3+) | Pattern | 2026-09-29 | 2026-10-02 | 4 | Not Started
Affiliate | 7 | Engage top 10-30 creators for retainers where applicable | Pattern | 2026-10-02 | 2026-10-09 | 8 | Not Started
Affiliate | 8 | Launch outreach | Pattern | 2026-10-09 | 2026-10-16 | 8 | Not Started
Affiliate | 9 | Creator retainers solidified | Pattern | 2026-10-16 | 2026-10-16 | 1 | Not Started
Affiliate | 10 | 20 new L3+ creator videos live | Pattern | 2026-10-16 | 2026-10-23 | 8 | Not Started
Advertising
Advertising | 1 | Set up TikTok Ads / GMV Max account and link to new shop | Pattern | 2026-09-28 | 2026-10-05 | 8 | Not Started
Advertising | 2 | Approve ad budget and advertising partnership | Brand | 2026-10-05 | 2026-10-06 | 2 | Not Started
Advertising | 3 | Confirm advertising operations | Pattern | 2026-10-06 | 2026-10-09 | 4 | Not Started
Advertising | 4 | Launch ads | Pattern | 2026-10-09 | 2026-10-09 | 1 | Not Started
Brand Handles
Brand Handles | 1 | Confirm marketing account structure (must include LIVE and AIGC) | Pattern/Brand | 2026-09-08 | 2026-09-18 | 11 | Not Started
Brand Handles | 2 | Launch additional marketing accounts needed | Brand | 2026-09-18 | 2026-09-25 | 8 | Not Started
Brand Handles | 3 | Link marketing accounts to shop | Pattern/Brand | 2026-10-09 | 2026-10-11 | 3 | Not Started
Brand Handles | 4 | Align on plan for LIVE and AIGC content for marketing accounts | Pattern/Brand | 2026-10-11 | 2026-10-13 | 3 | Not Started